## Sprint Planning
Sprint Planning | Story | Task Planning | Priority
| As an administrator, I want to add dispensary for the doctor/staff to view. | 1. Design the UI | 1
2. Show hand draw mockup design to let customer have a review
3. Coding
4. Exploratory testing
| As a administrator, I want to view dispensary to keep track the dispensary details. | 1. Design the UI | 2
2. Show hand draw mockup design to let customer have a review
3. Coding
4. Exploratory testing
| As a administrator, I want to update dispensary details so that dispensary details is up-to-date. | 1. Design the UI | 3
2. Show hand draw mockup design to let customer have a review
3. Coding
4. Exploratory testing
| As a administrator, I want to delete dispensary so that outdated records not in the database. | 1. Design the UI | 4
2. Show hand draw mockup design to let customer have a review
3. Coding
4. Exploratory testing

## DailyScrumMeeting
Daily Scrum Meeting for Week | Developer Name | Task | Description
21 November 2016 Monday | Phua Teck Wai | Create Dispensary | Last week I done for the create main menu and research on dispensary task, today I will start to design the Create Dispensary Page and let all have a view on the design.
| Chin Wei Seng | Create Dispensary | Last week I done for the create patient menu and research on dispensary task, today I will start to design the Create Dispensary Page and let all have a view on the design.
| Tan Yan Kai | Delete Dispensary | Last week I done for the create patient menu and research on dispensary task, today I will start to design the Delete Dispensary Page and let all have a view on the design.
| Ng Hong yao | View Dispensary | Last week I done for the view patient menu and research on dispensary task, today I will start to design the View Dispensary Page and let all have a view on the design.
| Lim Yi Kun | Update Dispensary | Last week I done for the update patient menu and research on dispensary task, today I will start to design the Update Dispensary Page and let all have a view on the design.
Scrum Master Feedback |  |  | For the dispensary stock had mentioned last week there is many dispensary in the world. We can add in ID for each of the dispensary and name detail therefore easy to differentiate it with other.
22 November 2016 Tuesday | Phua Teck Wai | Create Dispensary | Yesterday I already done for design create dispensary page in hand draw mockup, today I will start coding for the create dispensary page. So far havent faced any problem yesterday.
| Chin Wei Seng | Create Dispensary | Yesterday I already done for design create dispensary page in hand draw mockup, today I will start coding for the create dispensary page. So far havent faced any problem yesterday.
| Tan Yan Kai | Delete Dispensary | Yesterday I already done for design delete dispensary page in hand draw mockup, today I will start coding for the delete dispensary page. So far havent faced any problem yesterday.
| Ng Hong yao | View Dispensary | Yesterday I already done for design view dispensary page in hand draw mockup, today I will start coding for the view dispensary page. So far havent faced any problem yesterday.
| Lim Yi Kun | Update Dispensary | Yesterday I already done for design update dispensary page in hand draw mockup, today I will start coding for the update dispensary page. So far havent faced any problem yesterday.
23 November 2016 Wednesday | Phua Teck Wai | Create Dispensary | Yesterday I already done for the coding for create dispensary page, today I will start to do the function for create dispensary. So far havent face any problem yesterday.
| Chin Wei Seng | Create Dispensary | Yesterday I already done for the coding for create dispensary page, today I will start to do the function for create dispensary. So far havent face any problem yesterday.
| Tan Yan Kai | Delete Dispensary | Yesterday I already done for the coding for delete dispensary page, today I will start to do the function for delete dispensary. So far havent face any problem yesterday.
| Ng Hong yao | View Dispensary | Yesterday I already done for the coding for view dispensary page, today I will start to do the function for view dispensary. So far havent face any problem yesterday.
| Lim Yi Kun | Update Dispensary | Yesterday I already done for the coding for update dispensary page, today I will start to do the function for update dispensary. So far havent face any problem yesterday.
24 November 2016 Thursday | Phua Teck Wai | Create Dispensary | Today I will continue to do the function for create dispensary module. The problem we faced yesterday is after click add there is no dispensary is added to database, will check what is the problem today.
| Chin Wei Seng | Create Dispensary | Today I will continue to do the function for create dispensary module. The problem we faced yesterday is after click add there is no dispensary is added to database, will check what is the problem today.
| Tan Yan Kai | Delete Dispensary | Today I will continue to do the function for delete dispensary module. The problem I faced yesterday is since there is no record in database, I cannot test the function is work well or not.
| Ng Hong yao | View Dispensary | Today I will continue to do the function for view dispensary module. The problem I faced yesterday is since there is no record in database, I cannot test the function is work well or not.
| Lim Yi Kun | Update Dispensary | Today I will continue to do the function for update dispensary module. The problem I faced yesterday is since there is no record in database, I cannot test the function is work well or not.
Scrum Master Feedback |  |  | Have to check create dispensary cannot add to database is software error or software fault.
25 November 2016 Friday | Phua Teck Wai | Create Dispensary | Yesterday I already done for the function for create dispensary module, today I will start to do the reseach for next week staff module. So far havent faced any problem yesterday.
| Chin Wei Seng | Create Dispensary | Yesterday I already done for the function for create dispensary module, today I will start to do the reseach for next week staff module. So far havent faced any problem yesterday.
| Tan Yan Kai | Delete Dispensary | Yesterday I already done for the function for delete dispensary module, today I will start to do the reseach for next week staff module. So far havent faced any problem yesterday.
| Ng Hong yao | View Dispensary | Yesterday I already done for the function for view dispensary module, today I will start to do the reseach for next week staff module. So far havent faced any problem yesterday.
| Lim Yi Kun | Update Dispensary | Yesterday I already done for the function for update dispensary module, today I will start to do the reseach for next week staff module. So far havent faced any problem yesterday.

## SprintReviewMeeting
Sprint Review Meeting | Description | Feedback from other
Add Dispensary | As an administrator, i want to add dispensary for the doctor/staff to view. | Dispensary detail must be match with database and common sense.
View Dispensary | As a administrator, i want to view dispensary to keep track the dispensary details. | To make sure all dispensary detail is inside the view patient module.
Update Dispensary | As a administrator, i want to update dispensary details so that dispensary details is up-to-date. | When update dispensary must be update dispensary database too.
Delete Dispensary | As a administrator, i want to delete patient so that outdated records not in the database. | To delete a row record in the database if the record no longer used.

## Retrospective
Retrospective | Description | Encountered problem | Action will be taken on next sprint
Add Dispensary | As an administrator, i want to add dispensary for the doctor/staff to view. | Not able to complete the task on expected time frame. | Move on to next module when error cannot be solve in limited time.
View Dispensary | As a administrator, i want to view dispensary to keep track the dispensary details. | This task is work well because it's can let user view overall dispensary detail in a list.
Update Dispensary | As a administrator, i want to update dispensary details so that dispensary details is up-to-date. | This task is work well because it's update the medicine and show confirmation dialog and update to database too.
Delete Dispensary | As a administrator, i want to delete patient so that outdated records not in the database. | This task is work well because it's delete the medicine records that the medicine no longer sell.