## Sprint Planning
Sprint Planning | Story | Task Planning | Priority
| As an administrator, I want to view all the modules so that I can access to each modules. | 1. Design the UI | 1
2. Link all the navigation
| As an administrator, i want to add patient for the doctor/staff to view. | 1. Design the UI | 2
2. Code
3. Meet with customers
4. Exploratory testing
| As an administrator, i want to view patient to keep track the patient details. | 1. Design the UI | 3
2. Code
3. Meet with customers
4. Exploratory testing
| As an administrator, i want to update patient details so that patient details is up-to-date | 1. Design the UI | 4
2. Code
3. Meet with customers
4. Exploratory testing

## DailyScrumMeeting
Daily Scrum Meeting | Developer Name | Task | Description | Issue Faced | Done for Yesterday
Friday | Phua Teck Wai | Main Menu | Today I will start to design Main Menu, first I will draw it on paper to let customer and team have a look on the design for Main Menu. | No | No
| Chin Wei Seng | Main Menu | Today I will assits team member Phua Teck Wai to design the Main Menu. | No | No
| Tan Yan Kai | Create Patient | Today I will start to design the Create Patient page and let all have a view on the design. | No | No
| Ng Hong yao | View Patient | Today I will start to design the View Patient page and let all have a view on the design. | No | No
| Lim Yi Kun | Update Patient | Today I will start to design the Update Patient page and let all have a view on the design. | No | No
Saturday | Phua Teck Wai | Main Menu | Today I will start coding for the main menu. | No | Design Main Menu
| Chin Wei Seng | Create Patient | Today I will assits team member Tan Yan Kai to coding create patient page | No | Design Main Menu
| Tan Yan Kai | Create Patient | Today I will start coding for the Create Patient Page | Have to think logically about the way to create patient design | No
| Ng Hong yao | View Patient | Today I will start coding for the View Patient Page | Have to think logically about the way to view patient design | No
| Lim Yi Kun | Update Patient | Today I will start coding for the Update Patient Page | Have to think logically about the way to update patient design | No

## SprintReviewMeeting
Sprint Review Meeting | Description | Feedback from other
View All Module | when the modules selected, the UI of the modules will be display. | We can select module from main menu, so it must be very easy to navigate to other page.
Create Patient | As an administrator, i want to add patient for the doctor/staff to view. | Patient detail must be match with database and common sense
View Patient | As an administrator, i want to view patient to keep track the patient details. | To make sure all patient detail is inside the view patient module
Update Patient | As an administrator, i want to update patient details so that patient details is up-to-date | When update patient must be update patient database too.

## Retrospective
Retrospective | Description | Result | Action will be taken on next sprint
View All Module | when the modules selected, the UI of the modules will be display. | This task is work well because it's simple and very easy navigate to other page. | No
Create Patient | As an administrator, i want to add patient for the doctor/staff to view. | This task is doesn't work well because still have many patient detail havent add in to database. | Will add status to patient detail
View Patient | As an administrator, i want to view patient to keep track the patient details. | This task is doesn't work well because it's retrieve everything from database and without searching | Will add searching function
Update Patient | As an administrator, i want to update patient details so that patient details is up-to-date | This task is work well because it's update the patient and show confirmation dialog and update to database too. | No