## Sheet1
Week 7 Activity Log
[UserStory_Nr_from_Pivotal] | [Name_of_Uer Story] | User Story | Developers Name | Development Team | Duration
#134506521 | Create dispensary | As a administrator, I want to add dispensary for the doctor/staff to view. | Phua Teck Wai, Chin Wei Seng | Scrum Master, Developer | 21/11/2016 Monday - (2 hours)
22/11/2016 Tuesday - (2 hours)
23/11/2016 Wednesday - (2 hours)
24/11/2016 Thursday - (3 hours)
25/11/2016 Friday - (2 hours)
#134506559 | Delete dispensary | As a administrator, I want to delete patient so that outdated records not in the database. | Tan Yan Kai | Developer | 21/11/2016 Monday - (2 hours)
22/11/2016 Tuesday - (2 hours)
23/11/2016 Wednesday - (2 hours)
24/11/2016 Thursday - (3 hours)
25/11/2016 Friday - (2 hours)
#134506545 | View dispensary | As a administrator, I want to view dispensary to keep track the dispensary details. | Ng Hong yao | Developer | 21/11/2016 Monday - (2 hours)
22/11/2016 Tuesday - (2 hours)
23/11/2016 Wednesday - (2 hours)
24/11/2016 Thursday - (3 hours)
25/11/2016 Friday - (2 hours)
#134506535 | Update dispensary | As a administrator, I want to update dispensary details so that dispensary details is up-to-date | Lim Yi Kun | Developer | 21/11/2016 Monday - (2 hours)
22/11/2016 Tuesday - (2 hours)
23/11/2016 Wednesday - (2 hours)
24/11/2016 Thursday - (3 hours)
25/11/2016 Friday - (2 hours)