## Sprint Planning
Sprint Planning | Story | Task Planning | Priority
| As an administrator, I want to register account so that I can use my own username and password log in to system to view all the detail in the system. | 1. Design the UI | 1
2. Show hand draw mockup design to let customer have a review
3. Coding
4. Exploratory testing
| As a administrator, I want to update my own personal detail or change password so that I can retrieved back my personal detail or password. | 1. Design the UI | 2
2. Show hand draw mockup design to let customer have a review
3. Coding
4. Exploratory testing

## DailyScrumMeeting
Daily Scrum Meeting for Week | Developer Name | Task | Description
12 December 2016 Monday | Phua Teck Wai | Registration Administrative | Last week I done for the login page and research on registration administrative task, today I will start to design the Registration Page and let all have a view on the design.
| Chin Wei Seng | Update Administrative | Last week I done for the payment page and research on update administrative task, today I will start to design the Update Registration Page and let all have a view on the design.
| Tan Yan Kai | Registration Administrative | Last week I done for the login page and research on registration administrative task, today I will start to design the Registration Page and let all have a view on the design.
| Ng Hong yao | Update Administrative | Last week I done for the payment page and research on update administrative task, today I will start to design the Update Registration Page and let all have a view on the design.
| Lim Yi Kun | Update Administrative | Last week I done for the payment page and research on update administrative task, today I will start to design the Update Registration Page and let all have a view on the design.
13 December 2016 Tuesday | Phua Teck Wai | Registration Administrative | Yesterday I already done for design registration page in hand draw mockup, today I will start coding for the registration page. So far havent faced any problem yesterday.
| Chin Wei Seng | Update Administrative | Yesterday I already done for design update admin page in hand draw mockup, today I will start coding for the update admin page. So far havent faced any problem yesterday.
| Tan Yan Kai | Registration Administrative | Yesterday I already done for design registration page in hand draw mockup, today I will start function for the registration page. So far havent faced any problem yesterday.
| Ng Hong yao | Update Administrative | Yesterday I already done for design update admin page in hand draw mockup, today I will start to do the function for update admin. So far havent faced any problem yesterday.
| Lim Yi Kun | Update Administrative | Yesterday I already done for design update admin page in hand draw mockup, today I will start to do the function for update admin. So far havent faced any problem yesterday.
Scrum Master Feedback |  |  | Admin Detail is no enough please add more detail about admin.
14 December 2016 Wednesday | Phua Teck Wai | Registration Administrative | Yesterday I already done for the coding for registration page and add more detail about admin, today I will start to do the function for registration page. So far havent faced any problem yesterday.
| Chin Wei Seng | Update Administrative | Yesterday I already done for the coding for update admin page, today I will start to do the function for update admin page. So far havent faced any problem yesterday.
| Tan Yan Kai | Registration Administrative | Today I will continue to do the function for registration page. The problem I faced yesterday is the admin detail cannot add in to database.
| Ng Hong yao | Update Administrative | Today I will continue to do the function for update admin page. The problem I faced yesterday is because there have no record in database therefore cannot test the function is work well or not.
| Lim Yi Kun | Update Administrative | Today I will continue to do the function for update admin page. The problem I faced yesterday is because there have no record in database therefore cannot test the function is work well or not.
Scrum Master Feedback |  |  | Have to check create admin detail cannot add to database is software error or is software fault.
15 December 2016 Thursday | Phua Teck Wai | Registration Administrative | Today I will continue to do the function for registration page. So far havent faced any problem yesterday.
| Chin Wei Seng | Update Administrative | The update admin page is done already, so today I will assit to other team member to do the registration page. So far havent faced any problem yesterday.
| Tan Yan Kai | Registration Administrative | Today I will continue to do the function for registration page. So far havent faced any problem yesterday.
| Ng Hong yao | Update Administrative | The update admin page is done already, so today I will assit to other team member to do the registration page. So far havent faced any problem yesterday.
| Lim Yi Kun | Update Administrative | The update admin page is done already, so today I will assit to other team member to do the registration page. So far havent faced any problem yesterday.
16 December 2016 Friday | Phua Teck Wai | Registration Administrative | Yesterday I already done for the function for registration today I will start to do the testing for all module. So far havent faced any problem yesterday.
| Chin Wei Seng | Update Administrative | Yesterday I already done for the function for registration today I will start to do the testing for all module. So far havent faced any problem yesterday.
| Tan Yan Kai | Registration Administrative | Yesterday I already done for the function for registration today I will start to do the testing for all module. So far havent faced any problem yesterday.
| Ng Hong yao | Update Administrative | Yesterday I already done for the function for registration today I will start to do the testing for all module. So far havent faced any problem yesterday.
| Lim Yi Kun | Update Administrative | Yesterday I already done for the function for registration today I will start to do the testing for all module. So far havent faced any problem yesterday.

## SprintReviewMeeting
Sprint Review Meeting | Description | Feedback from other
Add Staff | As an administrator, i want to register my own personal account. | There are no any existing account can be register with same username.
View Staff | As a administrator, i want to update my own personal account | Admin detail must be match with database and common sense.
Update Staff

## Retrospective
Retrospective | Description | Encountered problem | Action will be taken on next sprint
Registration Administrative | As an administrator, i want to register my own personal account to secure the system. | This task is very complicated and hard to do | get solution from online source and ask team member to help
Update Administrative | As a administrator, i want update my personal detail if the there are some need to change or update. | The task is work well because its update successfully.