## Sprint Planning
Sprint Planning | Story | Task Planning | Priority
| As an administrator, I want to view all the modules so that I can access to each modules. | 1. Design the UI | 1
2. Show hand draw mockup design to let customer have a review
3. Coding
4. Link all the navigation
| As an administrator, i want to add patient for the doctor/staff to view. | 1. Design the UI | 2
2. Show hand draw mockup design to let customer have a review
3. Coding
4. Exploratory testing
| As an administrator, i want to view patient to keep track the patient details. | 1. Design the UI | 3
2. Show hand draw mockup design to let customer have a review
3. Coding
4. Exploratory testing
| As an administrator, i want to update patient details so that patient details is up-to-date | 1. Design the UI | 4
2. Show hand draw mockup design to let customer have a review
3. Coding
4. Exploratory testing

## DailyScrumMeeting
Daily Scrum Meeting | Developer Name | Task | Description | Issue Faced | Done for Yesterday
14 November 2016 Monday | Phua Teck Wai | Main Menu | Today I will start to design Main Menu, first I will draw it on paper to let customer and team have a look on the design for Main Menu. | No | No
| Chin Wei Seng | Main Menu | Today I will start to design the Create Patient page and let all have a view on the design. | No | No
| Tan Yan Kai | Create Patient | Today I will start to design the Create Patient page and let all have a view on the design. | No | No
| Ng Hong yao | View Patient | Today I will start to design the View Patient page and let all have a view on the design. | No | No
| Lim Yi Kun | Update Patient | Today I will start to design the Update Patient page and let all have a view on the design. | No | No
15 November 2016 Tuesday | Phua Teck Wai | Main Menu | Yesterday I already done for Design Main Menu in hand draw mockup, today I will start coding for the main menu. So far havent face any problem yesterday. | No | Design Main Menu
| Chin Wei Seng | Create Patient | Yesterday I already done for Design Create Patient Page in hand draw mockup, today I will assits team member Tan Yan Kai to coding create patient page. The problem we faced yesterday is have to think logically about the way to create patient design but the problem is already solved by all together. | No | Design Main Menu
| Tan Yan Kai | Create Patient | Yesterday I already done for Design Create Patient Page in hand draw mockup, today I will start coding for the Create Patient Page. The problem we faced yesterday is have to think logically about the way to create patient design but the problem is already solved by all together. | Have to think logically about the way to create patient design | No
| Ng Hong yao | View Patient | Yesterday I already done for Design View Patient Page in hand draw mockup, today I will start coding for the View Patient Page. The problem I faced yesterday is have to think logically about the way to view patient design but the problem is already solved by all together. | Have to think logically about the way to view patient design | No
| Lim Yi Kun | Update Patient | Yesterday I already done for Design Update Patient Page in hand draw mockup, today I will start coding for the Update Patient Page. The problem I faced yesterday is have to think logically about the way to update patient design but the problem is already solved by all. | Have to think logically about the way to update patient design | No
Scrum Master Feedback |  |  | Have to online research to know the logic flow about how is the clinic system is work.
16 November 2016 Wednesday | Phua Teck Wai | Main Menu | Yesterday I already done for the coding for main menu, today I will start to do the function for main menu. So far havent face any problem yesterday.
| Chin Wei Seng | Create Patient | Today I will continue to coding for the create patient menu, so far havent face any problem yesterday. Besides that, I will do more online researching to search how the clinic system is work.
| Tan Yan Kai | Create Patient | Today I will continue to coding for the create patient menu, so far havent face any problem yesterday.
| Ng Hong yao | View Patient | Today I will continue to coding for the view patient menu, so far havent face any problem yesterday.
| Lim Yi Kun | Update Patient | Today I will continue to coding for the update patient menu, so far havent face any problem yesterday.
17 November 2016 Thursday | Phua Teck Wai | Main Menu | Yesterday I already done for the function for main menu. I will start to do the research for next week task which is dispensary module. So far havent faced any problem yesterday.
| Chin Wei Seng | Create Patient | Yesterday I already done for coding create patient menu, today I will do function for the create patient module. So far havent faced any problem yesterday.
| Tan Yan Kai | Create Patient | Yesterday I already done for coding create patient menu, today I will do function for the create patient module. So far havent faced any problem yesterday.
| Ng Hong yao | View Patient | Yesterday I already done for coding view patient menu, today I will do function for the view patient module. So far havent faced any problem yesterday.
| Lim Yi Kun | Update Patient | Yesterday I already done for coding update patient menu, today I will do function for the update patient module. So far havent faced any problem yesterday.
Scrum Master Feedback |  |  | After done the coding function please check for next week module and make a research on it.
18 November 2016 Friday | Phua Teck Wai | Research | Today I will continue to do research for dispensary module. The problem I faced yesterday is there are so many dispensary is same look in the world, how can we differentiate it with other.
| Chin Wei Seng | Create Patient | Yesterday I already done for the function for create patient module, today I will start to do the reseach for next week dispensary module. So far havent faced any problem yesterday.
| Tan Yan Kai | Create Patient | Yesterday I already done for the function for create patient module, today I will start to do the reseach for next week dispensary module. So far havent faced any problem yesterday.
| Ng Hong yao | View Patient | Yesterday I already done for the function for view patient module, today I will start to do the reseach for next week dispensary module. So far havent faced any problem yesterday.
| Lim Yi Kun | Update Patient | Yesterday I already done for the function for update patient module, today I will start to do the reseach for next week dispensary module. So far havent faced any problem yesterday.

## SprintReviewMeeting
Sprint Review Meeting | Description | Feedback from other
View All Module | when the modules selected, the UI of the modules will be display. | We can select module from main menu, so it must be very easy to navigate to other page.
Create Patient | As an administrator, i want to add patient for the doctor/staff to view. | Patient detail must be match with database and common sense
View Patient | As an administrator, i want to view patient to keep track the patient details. | To make sure all patient detail is inside the view patient module
Update Patient | As an administrator, i want to update patient details so that patient details is up-to-date | When update patient must be update patient database too.

## Retrospective
Retrospective | Description | Encountered problem | Action will be taken on next sprint
View All Module | when the modules selected, the UI of the modules will be display. | The design is doesn’t not meet customer expectation. | Should come out and discuss with customer together and draw it in hand draw mockup to let customer have a brief view for the how the system design is look like.
Create Patient | As an administrator, i want to add patient for the doctor/staff to view. | There are many bugs that found when try to add patient details. | Need to understand the business logic so that only can know which data must included and which data is don’t need.
View Patient | As an administrator, i want to view patient to keep track the patient details. | Not able to complete the task on expected time frame because of don’t really understand the business logic how its flow. | Discuss with team member and customer to get the detail how the task work and solve it together. Don’t wasting the time with searching how to solve with solo, should ask other people how to solve also.
Update Patient | As an administrator, i want to update patient details so that patient details is up-to-date | Don’t know what to do after the work is done. | Understand the importance for the use of of work tracking in order to complete task in given time frame, We can know what to do immediately while working hour.