## Sprint Planning
Sprint Planning | Story | Task Planning | Priority
| As an administrator, I want to add staff for the doctor/staff to view. | 1. Design the UI | 1
2. Show hand draw mockup design to let customer have a review
3. Coding
4. Exploratory testing
| As a administrator, I want to view staff to keep track the dispensary details. | 1. Design the UI | 2
2. Show hand draw mockup design to let customer have a review
3. Coding
4. Exploratory testing
| As a administrator, I want to update staff details so that staff details is up-to-date. | 1. Design the UI | 3
2. Show hand draw mockup design to let customer have a review
3. Coding
4. Exploratory testing

## DailyScrumMeeting
Daily Scrum Meeting for Week | Developer Name | Task | Description
28 November 2016 Monday | Phua Teck Wai | Add Staff | Last week I done for the create dispensary and research on staff task, today I will start to design the Add Staff Page and let all have a view on the design.
| Chin Wei Seng | View Staff | Last week I done for the create dispensary and research on staff task, today I will start to design the View Staff Page and let all have a view on the design.
| Tan Yan Kai | View Staff | Last week I done for the delete dispensary and research on staff task, today I will start to design the View Staff Page and let all have a view on the design.
| Ng Hong yao | Update Staff | Last week I done for the view dispensary and research on staff task, today I will start to design the Update Staff Page and let all have a view on the design.
| Lim Yi Kun | Update Staff | Last week I done for the update dispensary and research on staff task, today I will start to design the Update Staff Page and let all have a view on the design.
29 November 2016 Tuesday | Phua Teck Wai | Add Staff | Yesterday I already done for design add staff page in hand draw mockup, today I will start coding for the create staff page. So far havent faced any problem yesterday.
| Chin Wei Seng | View Staff | Yesterday I already done for design view staff page in hand draw mockup, today I will start coding for the view staff page. So far havent faced any problem yesterday.
| Tan Yan Kai | View Staff | Yesterday I already done for design view staff page in hand draw mockup, today I will start coding for the view staff page. So far havent faced any problem yesterday.
| Ng Hong yao | Update Staff | Yesterday I already done for design update staff page in hand draw mockup, today I will start coding for the update staff page. So far havent faced any problem yesterday.
| Lim Yi Kun | Update Staff | Yesterday I already done for design update staff page in hand draw mockup, today I will start coding for the update staff page. So far havent faced any problem yesterday.
Scrum Master Feedback |  |  | Staff Detail is no enough please add more detail about staff.
30 November 2016 Wednesday | Phua Teck Wai | Add Staff | Yesterday I already done for the coding for add staff page and add more detail to staff, today I will start to do the function for add staff. So far havent faced any problem yesterday.
| Chin Wei Seng | View Staff | Yesterday I already done for the coding for view staff page, today I will start to do the function for view staff So far havent faced any problem yesterday.
| Tan Yan Kai | View Staff | Yesterday I already done for the coding for view staff page, today I will start to do the function for view staff So far havent faced any problem yesterday.
| Ng Hong yao | Update Staff | Yesterday I already done for the coding for update staff page, today I will start to do the function for update staff So far havent faced any problem yesterday.
| Lim Yi Kun | Update Staff | Yesterday I already done for the coding for update staff page, today I will start to do the function for update staff So far havent faced any problem yesterday.
1 December 2016 Thursday | Phua Teck Wai | Add Staff | Today I will continue to do the function for add staff module. So far havent faced any problem yesterday.
| Chin Wei Seng | View Staff | Today I will continue to do the function for view staff module. The problem we faced yesterday is have to filter which record can show in the list let all view and which record doesn't need to show out.
| Tan Yan Kai | View Staff | Today I will continue to do the function for view staff module. The problem we faced yesterday is have to filter which record can show in the list let all view and which record doesn't need to show out.
| Ng Hong yao | Update Staff | Today I will continue to do the function for update staff module. The problem I faced yesterday using which specifed to update the record
| Lim Yi Kun | Update Staff | Today I will continue to do the function for update staff module. The problem I faced yesterday using which specifed to update the record
Scrum Master Feedback |  |  | For the record filter only show the important detail, those useless record can keep in database doesn't need to show out. For the update staff module use ID as the specified to update the record.
1 December 2016 Friday | Phua Teck Wai | Add Staff | Yesterday I already done for the function for add staff module, today I will start to do the reseach for next week login module. So far havent faced any problem yesterday.
| Chin Wei Seng | View Staff | Yesterday I already done for the function for view staff module, today I will start to do the reseach for next week payment module. So far havent faced any problem yesterday.
| Tan Yan Kai | View Staff | Yesterday I already done for the function for view staff module, today I will start to do the reseach for next week login module. So far havent faced any problem yesterday.
| Ng Hong yao | Update Staff | Yesterday I already done for the function for update staff module, today I will start to do the reseach for next week payment module. So far havent faced any problem yesterday.
| Lim Yi Kun | Update Staff | Yesterday I already done for the function for update staff module, today I will start to do the reseach for next week payment module. So far havent faced any problem yesterday.

## SprintReviewMeeting
Sprint Review Meeting | Description | Feedback from other
Add Staff | As an administrator, i want to add dispensary for the doctor/staff to view. | Staff detail must be match with database and common sense.
View Staff | As a administrator, i want to view dispensary to keep track the dispensary details. | To make sure all staff detail is inside the view staf module.
Update Staff | As a administrator, i want to update dispensary details so that dispensary details is up-to-date. | When update staff must be update staff database too.

## Retrospective
Retrospective | Description | Encountered problem | Action will be taken on next sprint
Add Staff | As an administrator, i want to add staff for the doctor/staff to view. | This task is work well because it's add succesfully and have previous experience about add to database.
View Staff | As a administrator, i want to view staff to keep track the dispensary details. | This task is work well because it's can let user view overall dispensary detail in a list.
Update Staff | As a administrator, i want to update staff details so that dispensary details is up-to-date. | This task is work well because it's update the medicine and show confirmation dialog and update to database too.