## Sprint Planning
Sprint Planning | Story | Task Planning | Priority
| As an administrator, I can log in to system with username and password so that the system need correct username and password only can log in. | 1. Design the UI | 1
2. Connect with Database
3. Coding
4. Exploratory testing
| As a administrator, I want to create payment for let customer pay the bill. | 1. Design the UI | 2
2. Show hand draw mockup design to let customer have a review
3. Coding
4. Exploratory testing

## DailyScrumMeeting
Daily Scrum Meeting for Week | Developer Name | Task | Description
5 December 2016 Monday | Phua Teck Wai | Login Page | Last week I done for the add staff and research on login task, today I will start to design the Login Page and let all have a view on the design.
| Chin Wei Seng | Payment | Last week I done for the view staff and research on payment task, today I will start to design the Payment Page and let all have a view on the design.
| Tan Yan Kai | Login Page | Last week I done for the view staff and research on login task, today I will start to design the Forget Password Page and let all have a view on the design.
| Ng Hong yao | Payment | Last week I done for the update staff and research on payment task, today I will start to do the calculation function for payment page.
| Lim Yi Kun | Payment | Last week I done for the update staff and research on payment task, today I will start to do the calculation function for payment page.
6 December 2016 Tuesday | Phua Teck Wai | Login Page | Yesterday I already done for design login page in hand draw mockup, today I will start coding for the login page. So far havent faced any problem yesterday.
| Chin Wei Seng | Payment | Yesterday I already done for design payment page in hand draw mockup, today I will start coding for the payment page. So far havent faced any problem yesterday.
| Tan Yan Kai | Login Page | Yesterday I already done for design forget password page in hand draw mockup, today I will start coding for the forget password page. So far havent faced any problem yesterday.
| Ng Hong yao | Payment | Today I wil continue to do the function for calculation function for payment page. So far havent faced any problem yesterday.
| Lim Yi Kun | Payment | Today I wil continue to do the function for calculation function for payment page. So far havent faced any problem yesterday.
7 December 2016 Wednesday | Phua Teck Wai | Login Page | Yesterday I already done for the coding for login page, today I will start to do the function for login page. So far havent faced any problem yesterday.
| Chin Wei Seng | Payment | Yesterday I already done for the coding for payment page, today I will start to do the function for payment page. So far havent faced any problem yesterday.
| Tan Yan Kai | Login Page | Yesterday I already done for the coding for forget password page, today I will start to do the function for forget password. So far havent faced any problem yesterday.
| Ng Hong yao | Payment | Yesterday I already done for the calculation function, today I will start to do the function for payment. So far havent faced any problem yesterday.
| Lim Yi Kun | Payment | Yesterday I already done for the calculation function, today I will start to do the function for payment. So far havent faced any problem yesterday.
8 December 2016 Thursday | Phua Teck Wai | Payment | The login page is done already, so today I will assit to other team member to do the payment module. So far havent faced any problem yesterday.
| Chin Wei Seng | Payment | Today I will continue to do the function for payment page. The problem I faced yesterday is the payment function doesn't work well.
| Tan Yan Kai | Payment | The login page is done already, so today I will assit to other team member to do the payment module. So far havent faced any problem yesterday.
| Ng Hong yao | Payment | Today I will continue to do the function for payment page. The problem I faced yesterday is the payment function doesn't work well.
| Lim Yi Kun | Payment | Today I will continue to do the function for payment page. The problem I faced yesterday is the payment function doesn't work well.
Scrum Master Feedback |  |  | For the payment module must have calculation to get the balance, receipt, validation.
9 December 2016 Friday | Phua Teck Wai | Payment | Yesterday I already done for the function for payment, today I will start to do the reseach for next week administrative module. So far havent faced any problem yesterday.
| Chin Wei Seng | Payment | Yesterday I already done for the function for payment, today I will start to do the reseach for next week administrative module. So far havent faced any problem yesterday.
| Tan Yan Kai | Payment | Yesterday I already done for the function for payment, today I will start to do the reseach for next week administrative module. So far havent faced any problem yesterday.
| Ng Hong yao | Payment | Yesterday I already done for the function for payment, today I will start to do the reseach for next week administrative module. So far havent faced any problem yesterday.
| Lim Yi Kun | Payment | Yesterday I already done for the function for payment, today I will start to do the reseach for next week administrative module. So far havent faced any problem yesterday.

## SprintReviewMeeting
Sprint Review Meeting | Description | Feedback from other
Add Staff | As an administrator, i want to log in to system | Username and Password must be correct and valid in database.
View Staff | As a administrator, i want to create payment so that customer can pay for the bill. | Payment must be clearly to defined the receipt.
Update Staff

## Retrospective
Retrospective | Description | Encountered problem | Action will be taken on next sprint
Login | As an administrator, i want to log in to the system. | not able to complete the task on expected time frame. | move on to next module when error cannot be solve in limited time.
Payment | As a administrator, i want to create payment for let customer pay the bill | There are many similar entity need to clearly link together | Have to Check one by one when create those entity.